## Schedule
Expo 2019 Items / Activities 11-30-18 R4 |  |  | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Council/Board
| Establish organization |  | June: Done
| Establish budget |  | June: In Process
| Establish Expo Committee schedule | Sherry | Sept: XXX
Treasurer
| Propose Expo budget to Council for 2020 | Sherry | June: XXX
| Track committed money & report monthly to committee | Sherry |  |  |  | XXX | XXX | XXX | XXX | XXX | XXX | XXX | XXX
| Complete Fairgrounds contract | Sherry | Sept: XXX; Oct: XXX
| Make down payment | Sherry | Oct: XXX
| Assist in developing all pricing | Sherry | Oct: XXX
| Assist merchandise pricing | Sherry | Oct: XXX
| Purchase insurance from National | Sherry | Oct: XXX
| Have registers/credit card machines ready | TBD | Feb: XXX; Mar: XXX
| Establish money requirements / cash available | TBD | Feb: XXX; Mar: XXX
| Have cash boxes with $ for each location | TBD | Mar: XXX
| Manage cash/credit card machines during Expo | TBD | Mar: XXX
| Prepare final report for Expo | TBD | Mar: XXX; Apr: XXX
Vendors
| Email to Vendors - repeat Vendors | Sherry | Sept: XXX; Oct: XXX
| Email to Vendors - new Vendors | Sherry | Sept: XXX; Oct: XXX
| Recruit donations from Vendors | Sherry |  |  |  | XXX | XXX | XXX | XXX | XXX | XXX | XXX
| Establish actual Vendor booth locations | Sherry | Sept: XXX; Oct: XXX; Nov: XXX; Dec: XXX; Jan: XXX; Feb: XXX
| Ensure contracts are returned | Sherry | Dec: XXX; Jan: XXX; Feb: XXX; Mar: XXX
| Sell Vendor advertising for Expo Program | Sherry | Dec: XXX; Jan: XXX
| Finalize Expo layout/Booth w/ Facilities Chair | Sherry | Jan: XXX
| Establish vendor packet material - fill packets | Sherry | Feb: XXX
| Manage Vendor setup at Expo | Sherry | Mar: XXX
| Recruit for next year & thank you letters | Sherry | Mar: XXX
Facilities
| Develop initial contract with Fairgrounds | Sherry | Sept: XXX
| Initial contract DWA pipe & drape | Sherry | Sept: XXX
| Develop Room block with Comfort Suites | Sherry | Sept: XXX
| Finalize booth & building layout w/DWA & Facilities chair | Sherry | Feb: XXX
| Develop after-hour security contract with Creative Security | Terry | Jan: XXX
| Contact Linn County Sheriff Reserve for day-time security | Terry | Jan: XXX
| Develop contract w/ Special Occasions for coat rack & stanchions | Terry | Jan: XXX
| Purchase classes/demonstration pond material | N/A | Jan: XXX; Feb: XXX
| Coordinate & print signage for Expo | Sherry | Nov: XXX
| Finalize setup schedule with Vendor chair & Fairgrounds | Sherry | Jan: XXX; Feb: XXX
| Manage All building setup | Tom | Mar: XXX
| Coordinate Creative Security times & staff during event | Tom | Mar: XXX
| Mark floors in Hall Wednesday before Expo | Tom | Mar: XXX
| Assist Vendor Chair with Vendor setup | Tom | Mar: XXX
| Open and Close Exhibit hall (first in last out) | Tom | Mar: XXX
| Manage building cleanup on Sunday | Tom | Mar: XXX
| Store items in Council storage | Tom | Mar: XXX
Voluneers ( suggest dividing this responsibility)
| Outreach to clubs for volunteers | Stumpf/Sherry | Nov: XXX; Dec: XXX; Jan: XXX; Feb: XXX
| Establish & coordate all volunteers for Expo | Stumpf/Sherry | Jan: XXX; Feb: XXX
| Develop central volunteer list of Club responsibilities | Stumpf/Sherry | Dec: XXX; Jan: XXX; Feb: XXX
| Establish time slots for volunteers where needed | Stumpf/Sherry | Dec: XXX; Jan: XXX; Feb: XXX
| Manage nametags for Volunteers, Tyers, & Vendors | Sherry | Jan: XXX; Feb: XXX
| Obtain Volunteer lists from each club | Stumpf | Jan: XXX; Feb: XXX
| Obtain Tyer list from Tyer Chair | Sherry | Jan: XXX; Feb: XXX
| Obtain Vendor list from Vendor Chair | Sherry | Jan: XXX; Feb: XXX
| Develop one nametag list (Excel) | Sherry | Jan: XXX; Feb: XXX
| Order nametags from PCNametag | Sherry | Jan: XXX; Feb: XXX
| Place ribbons with proper nametag | Sherry | Jan: XXX; Feb: XXX
| Distribute nametags to Tyer Chair, Class instructor Chair, Vendor Chair | Sherry | Jan: XXX; Feb: XXX
| Help direct volunteers to correct area at Expo | Tom | Mar: XXX
Live Auction / Silent Auction / Raffles
| Establish programs - numbers of items needed | TBD | Nov: XXX; Dec: XXX
| Raffles General-Silent Auction-Live Auction | TBD | Nov: XXX; Dec: XXX
| Special Raffles (develop as needed) | TBD | Nov: XXX; Dec: XXX
| Establish what club manages which program | TBD | Nov: XXX; Dec: XXX
| Solicitations of material (letters or emails or calls) | TBD | Nov: XXX; Dec: XXX; Jan: XXX; Feb: XXX
| FFF Clubs; Guides, Manufactures, Fly Shops etc. | TBD | Nov: XXX; Dec: XXX
| Divide responsibility for follow-up | TBD | Nov: XXX; Dec: XXX
| Cataloging items received, pricing and allotting to which program | TBD | Nov: XXX; Dec: XXX; Jan: XXX; Feb: XXX
| Expo cntr Rm 1 Finalize raffle/auction items | TBD
| Expo cntr Rm 1 - create raffle baskets; | TBD | Mar: XXX
| Log in activities at Expo (Thurs, Friday & Saturday) crewing | TBD | Mar: XXX
| Crewing for each program(During show) | TBD
| Raffles General | TBD | Jan: XXX; Feb: XXX; Mar: XXX
| Silent Auction | TBD | Jan: XXX; Feb: XXX; Mar: XXX
| Live Auction | TBD | Jan: XXX; Feb: XXX; Mar: XXX
| Special Raffles | TBD | Jan: XXX; Feb: XXX; Mar: XXX
| Crewing for Friday night reception - silent auction | TBD | Jan: XXX; Feb: XXX; Mar: XXX
| Crewing for Friday night Reception/Banquet | TBD | Jan: XXX; Feb: XXX; Mar: XXX
| People to display items during auction | TBD | Jan: XXX; Feb: XXX; Mar: XXX
| People to spot for auctioneer | TBD | Jan: XXX; Feb: XXX; Mar: XXX
| People to record sold price/bidder # | TBD | Jan: XXX; Feb: XXX; Mar: XXX
| People to total bids | TBD | Jan: XXX; Feb: XXX; Mar: XXX
| People to collect moneys | TBD | Jan: XXX; Feb: XXX; Mar: XXX
| People to collect items for bidders as paid | TBD | Jan: XXX; Feb: XXX; Mar: XXX
| Collection of unclaimed items and follow-up calls | TBD | Mar: XXX
| Thank you letters to participating donors | TBD | Apr: XXX
Expo fly Plates
| Establish list of fly plates to create for the Live auction | TBD | Nov: XXX; Dec: XXX
| Arange for the Framing | TBD | Nov: XXX; Dec: XXX
| Email requests for tyers to contribute flies for each plate | TBD | Nov: XXX; Dec: XXX
Advertising & Promotion
| Select Expo Fly for pin/logo | Hal | Sept: XXX; Nov: XXX
| Obtain art work for Expo Fly | TBD | Sept: XXX; Oct: XXX; Nov: XXX
| Design poster | TBD | Sept: XXX; Oct: XXX; Nov: XXX
| Print Poster | TBD | Oct: XXX; Nov: XXX
| Design Pin | TBD | Oct: XXX; Nov: XXX
| Save the date cards | Sherry | June: Done; Sept: Order More
| Distribute poster | TBD | Nov: XXX; Dec: XXX; Jan: XXX; Feb: XXX
| Develop Ad's for magazines | TBD | Dec: XXX
| Finalize which magazines to place ads | TBD | Dec: XXX
| Develop newspaper articles | Sherry | Dec: XXX
| Develop Expo Program | Sherry | Dec: XXX; Jan: XXX; Feb: XXX
| Develop/Sell Ads for Expo Program | Sherry | Dec: XXX; Jan: XXX; Feb: XXX
| Place Expo program on Web | Garren | Feb: XXX
Expo Printed Program content
| Tyers | Hal | Feb: XXX
| Classes | Dale | Feb: XXX
| Vendors | Sherry | Feb: XXX
| Youth program | Sherry/TU | Feb: XXX
| Casting Demo Schedule | TBD | Feb: XXX
| Vendor advertising | Sherry | Feb: XXX
Website
| Update website to new year, contacts, dates | Garren | Aug: XXX; Sept: XXX; Oct: XXX; Nov: XXX; Dec: XXX
| Update picture album from past year | Garren | Sept: XXX; Oct: XXX
| Update Expo pin | Garren | Sept: XXX; Oct: XXX; Nov: XXX
| Show hotels & RV campsites available | Garren | Sept: XXX; Oct: XXX; Nov: XXX
| Establish Shopping Cart management | Garren | Sept: XXX; Oct: XXX; Nov: XXX
| OPEN Shopping Cart | Garren | Jan: XXX
| Post classes, Reception tickets, packages | Garren | Sept: XXX; Oct: XXX; Nov: XXX; Dec: XXX; Jan: XXX
| Develop banners for other sites | Garren | Oct: XXX; Nov: XXX; Dec: XXX; Jan: XXX
| List Tyers | Garren | Nov: XXX; Dec: XXX; Jan: XXX
| List Vendors | Garren | Nov: XXX; Dec: XXX; Jan: XXX
| List Live Auction items | Garren | Feb: XXX
| Close online class orders for paying with check | Garren | Feb: XXX
| Close online ordering | Garren | Mar: XXX
Merchandise
| Contact shirt/cap vendors and select products | Keith | Sept: XXX; Oct: XXX; Nov: XXX
| Determine shirt/cap pricing | Keith | Sept: XXX; Oct: XXX; Nov: XXX
| Order pins (6 week factory time) ( Sundace marketing) | Sherry | Oct: XXX; Nov: XXX
| Order shirts & caps | Keith | Jan: XXX; Feb: XXX
| Manage name embroidery process | Keith | Jan: XXX; Feb: XXX
Merchandise Booth
| Develop merchandise list for booth | Sherry/Hillary | Dec: XXX; Jan: XXX
| Order fly boxes idf needed | Sherry/Hillary | Oct: N/A; Nov: N/A
| Purchase Merchandise needed | Sherry/Hillary | Nov: XXX; Dec: XXX; Jan: XXX
| Establish pricing | Sherry/Hillary | Nov: XXX; Dec: XXX; Jan: XXX
| Schedule and Gather Volunteers to run the booth | Sherry/Hillary | Feb: XXX
Tyers
| Mail invitations to Tyers | Hal | Sept: XXX
| Receive registration info | Hal | Sept: XXX; Oct: XXX; Nov: XXX; Dec: XXX
| Recruitment of fly boxes for silent auction | Hal | Dec: XXX; Jan: XXX
| Establish seating & tying times at Expo | Hal | Dec: XXX
| Recruitment of packet items for tyer packets | Hal | Dec: XXX; Jan: XXX
| Fill tyer packets | Hal | Feb: XXX; Mar: XXX
| Manage Tyers during Expo | Hal | Mar: XXX
| Collect flies from Tyers at show, if needed | Hal | Mar: XXX
| Prepare "thank you" to Tyers after Expo (email) | Hal | Mar: XXX; Apr: XXX
Classes - Classroom
| Recruit instructors & write descriptions | Dale | Sept: XXX; Oct: XXX; Nov: XXX
| Establish class prices | Dale | Sept: XXX; Oct: XXX; Nov: XXX; Dec: XXX
| Invite instructors to preorder merchandise | Dale | Jan: XXX
| Open classes for registration | Garren | Jan: XXX; Feb: XXX
| Develop & manage Class registration at Expo | Terry | Mar: XXX
| Send "thank you" to instructors (email?) | Dale | Mar: XXX; Apr: XXX
| Establish youth program & instructors | Shery/TU | Dec: XXX; Jan: XXX; Feb: XXX; Mar: XXX
Casting Classes
| Invite MCI/CI Csating instructors | Sherry | Nov: XXX; Dec: XXX; Jan: XXX; Feb: XXX; Mar: XXX
| Establish Casting schedule | Sherry/Dale | Dec: XXX; Jan: XXX; Feb: XXX; Mar: XXX
| Establish Casting Demo schedule | Sherry | Dec: XXX; Jan: XXX; Feb: XXX; Mar: XXX
Catering & Hospitality
| Develop Friday night reception/banquet menu | Sherry | Sept: XXX; Oct: XXX; Nov: XXX; Dec: XXX
| Establish pricing w/ Treasurer & Expo Chair | Sherry | Sept: XXX; Oct: XXX; Nov: XXX; Dec: XXX
| Print/Purchase Guest tickets - buy/print Generic ticket | Sherry | Dec: XXX; Jan: XXX
| Develop contract w/ food & beverage contractors | Sherry | Sept: XXX; Oct: XXX; Nov: XXX
| Manage food service at Expo | Sherry | Mar: XXX
| Concessions during Expo | Sherry | Mar: XXX
| Beverages for Expo participants - need to have water | Sherry | Mar: XXX
| Tyer/Vendor/Volunteer & Guests Banquet Reception (Friday) | Sherry | Mar: XXX
Friday night Reception & Banquet
| Develop program, MC | Sherry | Dec: XXX; Jan: XXX; Feb: XXX; Mar: XXX
| Develop program, MC (Auction part) | Sherry | Dec: XXX; Jan: XXX; Feb: XXX; Mar: XXX
| Develop & print Friday night Auction program | Sherry | Feb: XXX; Mar: XXX
| Auctioneer - 15- items (Agreement for dates) Will Godfrey | Sherry | June: May not Have Linve aucton; Feb: XXX; Mar: XXX
Programs during Expo
| Arrange for honor guard | Sherry | Dec: XXX; Jan: XXX; Feb: XXX
| Flag presentation each day | Eric | Mar: XXX
| Bagpipes | Keith | Dec: XXX; Jan: XXX; Feb: XXX
| Expo hall announcements | TBD | Mar: XXX
*

## Deadlines
Activity |  | Date
Deadline for Newsletter input | Sherry | 2018-12-06
Deadline for Newsletter to print | Xpress | 2018-12-07
Deadline for CMI/CI to comitt to Casting classes | Mary Ann | 2018-12-10
Newsletter Release | Sherry | 2018-12-14
Awards in newslettter, Articl on rerequest ofr done
the ore fly fisher
link to donation form
Facebook Maxine
Dave editor ---
join the ffi encourage it link at beginning
Open on line ordering, Shirts, hats, classes |  | 2018-01-12
Post Tyers Schdeule - Target Date |  | 2018-01-12
Post Classroom Classes |  | 2018-01-12
Post Casting Classes |  | 2018-01-12
Post Vendors & layout |  | 2018-01-12
Post Ticket Packages |  | 2018-01-12
Submit Voluteer names for Badging |  | 2018-01-12
Vendors |  | 2018-01-12
Volunteers |  | 2018-01-12
Tyers |  | 2018-01-12
Instructors |  | 2018-01-12
Flies due to Framers
Poster Plate | Sherry | 2018-01-12 | 2018-01-18
Legons Plate | Keith | 2018-01-15
Atlantic Salmon Plate (12 flies | Keith | 2018-01-15
Gild Plate | Sherry/Jerry | 2018-01-12
bill blacksone beete
2009 legons plate donating it back
Awards Deadline | Keith | 2018-01-15
Poster Plate flies due | Sherry | 2019-01-14
Nametag quotes | Sherry | 2018-01-25
Shirt Order Deadline | Dave M. | 2018-02-05 | ask him | was the 5th in 2018
Order nametags from PCNametag | Sherry | 2018-02-08
Close online class orders for paying with check | Garren | 2018-02-08
Deadline for Expo program input | Sherry | 2018-02-11
Close online ordering | Garren | 2018-02-16
Meetings
BOD & EXPO faca to face or conference as needed |  | 2018-02-16